## Tasks
Plan name | Tasks
Plan ID | XU8VTEII8Uqy7c_s8WXIdpcADP4k
Date of export | 23/04/2021
Task ID | Task Name | Bucket Name | Progress | Priority | Assigned To | Created By | Created Date | Start Date | Due Date | Late | Completed Date | Completed By | Description | Completed Checklist Items | Checklist Items | Labels
KFUjeEo-SkqqKKBc5E7rmJcACpRR | Plan beta phase | WP0 - Project Management | Not started | Important | Sheehy, Samuel | Sheehy, Samuel | 22/04/2021 |  | 27/05/2021 | false
CFuPIpHgG0OMQWpA3y2XhZcAEmCY | Deliver beta testing report | WP4 - Beta testing | Not started | Medium |  | Sheehy, Samuel | 22/04/2021 |  | 19/11/2021 | false | [5 empty] | Milestone
gNBTjUMns0iMNNsKSINPR5cAHnjn | Close beta phase | WP4 - Beta testing | Not started | Medium |  | Sheehy, Samuel | 22/04/2021 |  | 04/11/2021 | false | [5 empty] | Milestone
JT-vynsYW0mqZer7DtA5hJcAFgiX | Delete Heroku app | WP2B - AWS Deployment | Not started | Medium |  | Sheehy, Samuel | 22/04/2021 |  | 29/07/2021 | false | [5 empty] | Milestone
ZJsV0m3z1kiS3bO-EH3iypcADmRv | Deliver Validation Report | WP3 - Validation | Not started | Medium |  | Sheehy, Samuel | 22/04/2021 |  | 27/08/2021 | false | [5 empty] | Milestone
4NxYf3ROXE2lRuCXbvRB-JcAI2b4 | Present EV Minigrid integration to Stakeholders | WP1 - EV Minigrid Integration | Not started | Medium |  | Sheehy, Samuel | 22/04/2021 |  | 16/07/2021 | false | [5 empty] | Milestone
HwYUB9mNk0KqqVe8ST17WpcANZOu | Set up a CI pipeline as part of AWS deployment | WP2B - AWS Deployment | Not started | Medium |  | Sheehy, Samuel | 21/04/2021 |  |  | false
HpvSzO7ypEayJ7li3p0_zZcAD5A_ | Setup development environment for windows | WP2A - Tool Development | In progress | Important | Sheehy, Samuel | Sheehy, Samuel | 21/04/2021 |  | 07/05/2021 | false |  |  | Redis (?) Django Python enviornment | 0/2 | Be able to run headless analysis;Be able to work on visuals without needing RQ workers | Key Preperations
2sFcyPDrbEytA9XQjZP0b5cALxqV | Implement async views for charts | WP2A - Tool Development | Not started | Medium | Sheehy, Samuel | Sheehy, Samuel | 21/04/2021 |  | 07/05/2021 | false | [5 empty] | Key Preperations
61WsH9VcsE2UcR-SKZrz-pcAEgeE | Close Project for 2021 | WP0 - Project Management | Not started | Medium |  | Sheehy, Samuel | 21/04/2021 |  | 10/12/2021 | false | [5 empty] | Milestone
kNN0SjeH-EKqVPceGvBj-5cAMZCJ | Onboard Driss | WP0 - Project Management | Not started | Medium | Sheehy, Samuel | Sheehy, Samuel | 21/04/2021 |  | 28/05/2021 | false |  |  |  | 0/3 | setup development environment;django training;git training
qJuzurAHG0mHo-3U7x9Ws5cAMFmE | Launch of tool for EDF business units | WP5 - Commmercialisation | Not started | Medium |  | Sheehy, Samuel | 20/04/2021 |  | 18/10/2021 | false | [5 empty] | Milestone
F9DFyfePWEOBm1M2dXDBmZcADUb7 | Write a user guide | WP2A - Tool Development | Not started | Medium |  | Sheehy, Samuel | 20/04/2021 |  |  | false
lgFPTfZ8mkm-IljGV1iNf5cAIvjT | Source validation data | WP3 - Validation | Not started | Medium |  | Sheehy, Samuel | 20/04/2021 |  |  | false
wHy5tkiosEqCLZW9f6iuRJcAHrGG | Engage with solar car park operators | WP6 - Stakeholder Engagement | Not started | Medium |  | Sheehy, Samuel | 20/04/2021 |  |  | false
bRdhqZ0-_kmHcRF7bRmgYJcADNtj | Recruit beta testers | WP4 - Beta testing | Not started | Medium |  | Sheehy, Samuel | 20/04/2021 | 28/06/2021 | 27/08/2021 | false
1wXI77k74kqbvbc4rMVF_ZcALRam | Document validation for minigrid tool | WP1 - EV Minigrid Integration | Not started | Medium |  | Sheehy, Samuel | 20/04/2021 |  |  | false
Uno48H6nakGS1KRSTA2pPZcAAp7R | Integrate minigrid into app | WP1 - EV Minigrid Integration | Not started | Medium |  | Sheehy, Samuel | 20/04/2021 |  |  | false
rK8MnbYWskWEEQQ02oBTC5cAGb7_ | Design UI for minigrid | WP1 - EV Minigrid Integration | Not started | Medium |  | Sheehy, Samuel | 20/04/2021 |  |  | false
qVUjzJJcM0agXGXypVCFsJcAB_7A | Write tests for minigrid package | WP1 - EV Minigrid Integration | Not started | Medium |  | Sheehy, Samuel | 20/04/2021 |  |  | false
d4g7cWFpS0SbRdDb5Csi8JcAI4Xm | Prepare API specification for interfacing tool with app | WP1 - EV Minigrid Integration | Not started | Medium |  | Sheehy, Samuel | 20/04/2021 |  |  | false
9CDgd3mqqEWW6ftFD0aM0JcANIAn | Allow accounting for several types of days | WP2A - Tool Development | Not started | Medium |  | Sheehy, Samuel | 20/04/2021 |  |  | false
IaZZUKuuRkGi0-E2JtgyeZcAIO1o | Register app on edflabs domain | WP2A - Tool Development | Not started | Medium |  | Sheehy, Samuel | 20/04/2021 |  |  | false
vJrR8MgV00K5f69yfaW7gpcAMhGo | Migrate tool from Heroku to AWS | WP2B - AWS Deployment | Not started | Medium |  | Sheehy, Samuel | 20/04/2021 |  |  | false
JjTN9XjmEEG47UAaPJMVSpcAFywb | Add tests to key functions/methods in tool | WP2A - Tool Development | Not started | Medium |  | Sheehy, Samuel | 20/04/2021 |  |  | false
_AyjPf3Q5k6Oi27hviQWMZcAHcU- | Add coverage measurment of function testing | WP2A - Tool Development | Not started | Medium |  | Sheehy, Samuel | 20/04/2021 |  |  | false
Eh1W6-zIpUeV5X_vtgwjwZcAC1Ct | Create Sequence Diagram for web application | WP2A - Tool Development | Not started | Medium |  | Sheehy, Samuel | 20/04/2021 |  |  | false
6bfoKx1bF0WA6WDPBl5hMpcAIMuV | Create Process Diagram for analysis | WP2A - Tool Development | Not started | Medium |  | Sheehy, Samuel | 20/04/2021 |  |  | false
OugIcswPak6DNQl0bCWpOJcAOdaJ | Onboard Uche | WP0 - Project Management | Not started | Medium | Sheehy, Samuel | Sheehy, Samuel | 20/04/2021 | 10/05/2021 | 14/05/2021 | false |  |  |  | 0/3 | Setup development environment;django training;git training
PjQQaDl910uRjnWA3GEpA5cAHuMQ | Prepare updates for Rebecca | WP6 - Stakeholder Engagement | Not started | Medium |  | Sheehy, Samuel | 20/04/2021 |  |  | false
EiViW6GUakWY99_-a9t_HZcAGPFb | Define licensing of tool and business model | WP5 - Commmercialisation | Not started | Medium |  | Sheehy, Samuel | 20/04/2021 |  |  | false
YqcnqTAMEk6lao2BwV-Q45cABaSe | Identify future bids and funding | WP5 - Commmercialisation | Not started | Medium |  | Sheehy, Samuel | 20/04/2021 |  |  | false | [5 empty] | Ongoing
UxTI_geawUCiR8P1wL2_YpcAIt3b | Track against budget | WP0 - Project Management | In progress | Medium | Sheehy, Samuel | Sheehy, Samuel | 20/04/2021 | 21/04/2021 | 10/12/2021 | false |  |  | Compare my time spent against what I have allocated to the project (for internal use) |  |  | Ongoing
vVEC7t1uOE-2Kp5Uv54ITZcAIoln | Do a Learn & Share session | WP6 - Stakeholder Engagement | Not started | Medium |  | Sheehy, Samuel | 20/04/2021 |  |  | false
WGAm3XiR0kSuSvts5InAvZcAEgfw | Find a customer | WP5 - Commmercialisation | Not started | Medium |  | Sheehy, Samuel | 20/04/2021 |  |  | false |  |  | EV team? WMO? I&C? DMEG? Pivot Power? Renewables? A meeting with each
QSOgvoPWK0mw2Jfaf7tlv5cABeap | Allocate sprint/time for bug fixing | WP4 - Beta testing | Not started | Medium |  | Sheehy, Samuel | 20/04/2021 |  |  | false
Vi9b0kax3UORWgtHLGA_gpcAB3Gj | Compare to Solar E-Mobility Tool | WP3 - Validation | Not started | Medium |  | Sheehy, Samuel | 20/04/2021 |  |  | false
cXX8Kg0GcUyWFfFQL8SgRpcAOJde | Define Use Cases | WP3 - Validation | Not started | Medium |  | Sheehy, Samuel | 20/04/2021 | 04/06/2021 | 25/06/2021 | false
OI1k652mpkGVjMJYUmjnhZcAPIG6 | Define Validation Cases | WP3 - Validation | Not started | Medium |  | Sheehy, Samuel | 20/04/2021 |  |  | false
mMDp4hPAAUiWqK1Dx7vQNJcAJOF- | Do a quality review | WP4 - Beta testing | Not started | Medium |  | Sheehy, Samuel | 20/04/2021 |  |  | false
tfvy6ebTIUGkgEfJqwna_5cAFquq | Define a sprint plan/methodology | WP0 - Project Management | Not started | Important | Sheehy, Samuel | Sheehy, Samuel | 20/04/2021 |  | 30/04/2021 | false
SD_ANTcuFkuwanara5kraJcAO008 | Define detailed workplan | WP1 - EV Minigrid Integration | Not started | Medium | Sheehy, Samuel | Sheehy, Samuel | 20/04/2021 |  | 07/05/2021 | false |  |  | Integrate into WPs details of this work once met with KAtie |  |  | Key Preperations
T2HF1xU9hEOpOsAIzS8M-5cAEway | Create a Risks and Issues log (spreadsheet: risk, mitigation, severity, likelihood) | WP0 - Project Management | In progress | Medium | Sheehy, Samuel | Sheehy, Samuel | 20/04/2021 |  | 30/04/2021 | false |  |  |  | 0/1 | Review with Red | Key Preperations
Qk6nFeYmykaMM2JBxyvK_pcAHDys | Setup a project plan (like Emma's for Celest) | WP0 - Project Management | In progress | Important | Sheehy, Samuel | Sheehy, Samuel | 20/04/2021 | 19/04/2021 | 30/04/2021 | false |  |  |  | 1/3 | Risk Register;Gantt chart;Completed Task board | Key Preperations
qIqE3mUYHUGqxXHnl1TqI5cAC2L5 | Set up fornightly meeting with PS team | WP0 - Project Management | Not started | Medium | Sheehy, Samuel | Sheehy, Samuel | 20/04/2021 |  | 30/04/2021 | false |  |  | Driss, Uche, Emma, Ali, ... | 0/3 | Send invites;Review with Red;Define the team | Key Preperations
a_Z9cyI3wUKMmmta87dOgZcAOSWP | Deliver 2021 work summary to Valérie | WP6 - Stakeholder Engagement | Not started | Medium | Sheehy, Samuel | Sheehy, Samuel | 20/04/2021 |  | 03/12/2021 | false |  |  | Include a presentation to senior stakeholders: Patrick Duperat, Stephanie Jumel, internation R&D centres... |  |  | Milestone
11rA-gs5mEOpkPjEuOAotJcACdF9 | Deliver pitch deck for the tool to Redwan for review | WP5 - Commmercialisation | Not started | Medium |  | Sheehy, Samuel | 20/04/2021 |  | 02/07/2021 | false | [5 empty] | Milestone
03zw8RZOuUWedc_8G_iV1ZcAJg9i | Complete refactor of analysis code | WP2A - Tool Development | Not started | Medium |  | Sheehy, Samuel | 20/04/2021 |  | 04/06/2021 | false | [5 empty] | Milestone
hiXI_I4gWEOq8CHkylaqApcALuV4 | Officially launch beta phase | WP4 - Beta testing | Not started | Medium |  | Sheehy, Samuel | 20/04/2021 |  | 30/07/2021 | false | [5 empty] | Milestone
hW42SXvLQ0ihhtoVDVA7gZcAB09S | Complete EV Minigrid handover | WP1 - EV Minigrid Integration | Completed | Medium | Sheehy, Samuel | Sheehy, Samuel | 20/04/2021 | 22/04/2021 | 23/04/2021 | false | 23/04/2021 | Sheehy, Samuel |  |  |  | Milestone
a_6Qmf6C3UWrUtgSRGz5GJcAE40m | Attend Parking Silo group meeting | WP0 - Project Management | Not started | Medium | Sheehy, Samuel | Sheehy, Samuel | 20/04/2021 |  |  | false |  |  |  | 0/1 | Ask Justine when this is | Milestone
AXXgBQkulUaLAM_XwcGlb5cADXhz | Release stable version of the tool | WP2A - Tool Development | Not started | Medium |  | Sheehy, Samuel | 20/04/2021 |  | 30/07/2021 | false | [5 empty] | Milestone
J9sRFVXeTU-t2fNisXLVYZcAPpRz | Engage with ENEDIS (Ask Quentin Morel for contact) | WP6 - Stakeholder Engagement | Not started | Medium |  | Sheehy, Samuel | 23/04/2021 |  |  | false